## Sheet1
Scenario TID | Scenario Description | Test Case ID | Pre Condition | Steps to Execute | Expected Result | Actual Result | Status | Executed QA Name | Misc (Comments) | Pri
ST-LOGIN-001 | Login Page UI Verification | TC-LOGIN-001 | Browser opened to index.html | 1. Navigate to the login page. | Login card is centered, contains logo/title, username and password fields with floating labels, login button, demo credentials footer. All elements are visible and styled according to spec. | As expected; all elements present and styled correctly. | Pass | John Doe |  | High
2. Observe the page layout.
ST-LOGIN-002 | Successful Login – Admin | TC-LOGIN-002 | Login page loaded | 1. Enter username "admin". | User is redirected to dashboard.html. Top navbar shows username "admin" with "Admin" role badge. | Redirected to dashboard; navbar shows admin with Admin badge. | Pass | John Doe |  | High
2. Enter password "123".
3. Click Login button.
ST-LOGIN-003 | Successful Login – User | TC-LOGIN-003 | Login page loaded | 1. Enter username "user". | User is redirected to dashboard.html. Top navbar shows username "user" with "User" role badge. | Redirected to dashboard; navbar shows user with User badge. | Pass | John Doe |  | High
2. Enter password "123".
3. Click Login button.
ST-LOGIN-004 | Failed Login – Wrong Password | TC-LOGIN-004 | Login page loaded | 1. Enter username "admin". | Error message appears in red box: "Invalid username or password". User stays on login page. | Red error message displayed; user remains on login page. | Pass | John Doe |  | High
2. Enter password "wrong".
3. Click Login button.
ST-LOGIN-005 | Failed Login – Empty Fields | TC-LOGIN-005 | Login page loaded | 1. Leave username empty. | Error message appears: "Please fill in both fields". | Error message displayed as expected. | Pass | John Doe |  | Medium
2. Leave password empty.
3. Click Login button.
ST-LOGIN-006 | Demo Credentials Text | TC-LOGIN-006 | Login page loaded | 1. Scroll to bottom of login card. | Footer displays "Demo Credentials: Admin: admin / 123 User: user / 123". | Footer text matches exactly. | Pass | John Doe |  | Low
ST-LOGIN-007 | Responsive Login Page | TC-LOGIN-007 | Login page loaded | 1. Resize browser to tablet width (768px). | Login card shrinks appropriately, remains centered, inputs and button are readable. No horizontal overflow. | Card adjusts and remains centered; no overflow. | Pass | John Doe |  | Medium
2. Resize to mobile width (375px).
ST-DASH-001 | Dashboard Layout – Sidebar (Admin) | TC-DASH-001 | Logged in as admin | 1. Observe left sidebar. | Sidebar shows app logo, menu items: Dashboard, My Tasks, All Tasks, Create Task. Active item (Dashboard) is highlighted. | Sidebar displays all items; Dashboard highlighted. | Pass | John Doe |  | High
ST-DASH-002 | Dashboard Layout – Sidebar (User) | TC-DASH-002 | Logged in as user | 1. Observe left sidebar. | Sidebar shows menu items: Dashboard, My Tasks, Create Task. "All Tasks" is hidden. | "All Tasks" not present; other items visible. | Pass | John Doe |  | High
ST-DASH-003 | Top Navbar Elements | TC-DASH-003 | Logged in as admin | 1. Check top navbar. | Navbar displays correct page title (e.g., "Dashboard"), username "admin", role badge "Admin", logout button. | All elements present and correct. | Pass | John Doe |  | Medium
ST-DASH-004 | Task Summary Cards | TC-DASH-004 | At least one task exists in each status | 1. Navigate to Dashboard. | Four cards: Total Tasks, Pending, In Progress, Completed. Each shows appropriate icon and number. Hover effect works. | Cards display correct counts; hover effect works. | Pass | John Doe | Counts matched test data | High
ST-DASH-005 | Logout Functionality | TC-DASH-005 | Logged in | 1. Click Logout button. | User is redirected to login page (index.html). Session/local storage cleared. | Redirected to login; local storage cleared. | Pass | John Doe |  | High
ST-DASH-006 | Sidebar Collapse on Mobile | TC-DASH-006 | Logged in, desktop view | 1. Resize browser to mobile width (< 640px). | Sidebar collapses; hamburger icon appears. Clicking icon expands sidebar overlay. | Sidebar collapses; hamburger toggles overlay. | Pass | John Doe |  | Medium
ST-TASK-001 | Task Table Display | TC-TASK-001 | At least 3 tasks exist | 1. Go to My Tasks (user) or All Tasks (admin). | Table shows columns: ID, Title, Assigned To, Status, Created Date, Actions. Data rows display correctly. | Columns present; data rows visible. | Pass | John Doe |  | High
ST-TASK-002 | Status Badge Colors | TC-TASK-002 | Tasks with different statuses exist | 1. View task table. | Pending tasks have gray badge, In Progress orange, Completed green. | Badge colors match spec. | Pass | John Doe |  | Medium
ST-TASK-003 | Action Buttons Visibility (User) | TC-TASK-003 | Logged in as user, tasks assigned to user and to others exist | 1. View task table. | For tasks assigned to user: Edit, Delete icons visible. For tasks assigned to others: no action icons (or they are hidden/disabled). Assign button is not visible at all. | User sees icons only on own tasks; no Assign button anywhere. | Pass | John Doe |  | High
ST-TASK-004 | Action Buttons Visibility (Admin) | TC-TASK-004 | Logged in as admin | 1. View task table. | All tasks show Edit, Delete, and Assign icons. | All tasks have all three icons. | Pass | John Doe |  | High
ST-TASK-005 | Search Bar Filters Tasks | TC-TASK-005 | Multiple tasks exist with varying titles | 1. Enter text in search bar (e.g., "report"). | Table updates to show only tasks whose title contains "report". | Filtering works correctly. | Pass | John Doe |  | High
ST-TASK-006 | Status Filter Dropdown | TC-TASK-006 | Tasks with different statuses exist | 1. Select "Pending" from filter dropdown. | Table shows only tasks with status "Pending". | Only pending tasks displayed. | Pass | John Doe |  | High
ST-TASK-007 | Row Hover Highlight | TC-TASK-007 | Any task row | 1. Hover over a table row. | Background color of row changes subtly. | Hover effect applied. | Pass | John Doe |  | Low
ST-TASK-008 | Pagination / Scroll | TC-TASK-008 | More than 10 tasks exist | 1. View task table. | Table has scrollable body or pagination controls. All tasks accessible. | Scrollbar appears; all tasks visible. | Pass | John Doe |  | Medium
ST-MODAL-001 | Open Create Task Modal | TC-MODAL-001 | Logged in as any user | 1. Click "Create Task" in sidebar. | Modal appears centered with dark overlay, fade-in animation. Contains fields: Title, Description, Assign To, Status. | Modal opens with correct fields and animation. | Pass | John Doe |  | High
ST-MODAL-002 | Create Task – Validation Errors | TC-MODAL-002 | Create modal open | 1. Leave Title empty. | Error message "Title is required" appears under title field. Save button remains disabled. | Error shown; Save disabled. | Pass | John Doe |  | High
2. Click Save.
ST-MODAL-003 | Create Task – Success | TC-MODAL-003 | Create modal open | 1. Fill Title, Description, select user from Assign To, choose Status. | Modal closes. Green toast notification "Task created successfully" appears. New task appears in task table. | Modal closes; toast appears; new task in table. | Pass | John Doe |  | High
2. Click Save.
ST-MODAL-004 | Edit Task – Load Data | TC-MODAL-004 | Task exists | 1. Click Edit icon on a task. | Modal opens with task data pre-filled in all fields. | Fields pre-filled correctly. | Pass | John Doe |  | High
ST-MODAL-005 | Edit Task – Save Changes | TC-MODAL-005 | Edit modal open with changes | 1. Modify title, status, etc. | Modal closes. Green toast "Task updated" appears. Table reflects changes. | Changes saved; toast appears; table updated. | Pass | John Doe |  | High
2. Click Save.
ST-MODAL-006 | Cancel Button | TC-MODAL-006 | Create or Edit modal open | 1. Click Cancel. | Modal closes without any changes to task data. | Modal closes; no data change. | Pass | John Doe |  | Medium
ST-MODAL-007 | Assign To Dropdown Options | TC-MODAL-007 | Create modal open | 1. Click Assign To dropdown. | Dropdown lists all available users (e.g., "admin", "user"). | Both users listed. | Pass | John Doe |  | Medium
ST-DELETE-001 | Delete Task – Confirmation | TC-DELETE-001 | Task exists | 1. Click Delete icon on a task. | Confirmation modal appears with "Are you sure?" and Yes/No buttons. | Confirmation modal displayed. | Pass | John Doe |  | High
ST-DELETE-002 | Delete Task – Cancel | TC-DELETE-002 | Confirmation modal open | 1. Click No. | Modal closes, task remains unchanged. | Modal closes; task still present. | Pass | John Doe |  | Medium
ST-DELETE-003 | Delete Task – Confirm | TC-DELETE-003 | Confirmation modal open | 1. Click Yes. | Task is removed from table. Red toast "Task deleted" appears. | Task removed; red toast shown. | Pass | John Doe |  | High
ST-ROLE-001 | User attempts to delete others' task | TC-ROLE-001 | Logged in as user, task assigned to admin exists | 1. From My Tasks, try to locate task not assigned to user (should not be visible). If visible (due to bug), click Delete. | Either the Delete icon is not present, or if present and clicked, an error toast "Unauthorized Action" appears and task is not deleted. | Delete icon not present for others' tasks; no unauthorized action possible. | Pass | John Doe |  | High
ST-ROLE-002 | User attempts to edit others' task | TC-ROLE-002 | Logged in as user, task assigned to admin exists (if visible) | 1. Try to edit a task not assigned to user. | Edit icon not present, or if present and clicked, error toast appears. | Edit icon not present. | Pass | John Doe |  | High
ST-ROLE-003 | Admin assigns task to user | TC-ROLE-003 | Logged in as admin, task exists | 1. Click Assign on a task. | Task's Assigned To updates. | Assigned To updated correctly. | Pass | John Doe |  | High
2. Select different user from modal.
3. Save.
ST-ROLE-004 | User cannot see "All Tasks" menu | TC-ROLE-004 | Logged in as user | 1. Check sidebar menu. | "All Tasks" is not present. | Menu item absent. | Pass | John Doe |  | High
ST-ALERT-001 | Toast disappears after 3 seconds | TC-ALERT-001 | Perform any action that triggers a toast (e.g., create task) | 1. Wait 3 seconds. | Toast fades out and disappears. | Toast disappeared after ~3s. | Pass | John Doe |  | Medium
ST-ALERT-002 | Success and Error Toast Colors | TC-ALERT-002 | Trigger a success toast (create) and an error toast (e.g., unauthorized action) | 1. Observe toast background colors. | Success toast is green, error toast is red. | Colors as expected. | Pass | John Doe |  | Low
ST-STORAGE-001 | Tasks persist after refresh | TC-STORAGE-001 | At least one task exists | 1. Refresh dashboard page. | All tasks remain visible, no data loss. | Tasks still present after refresh. | Pass | John Doe |  | High
ST-STORAGE-002 | Login session persists after refresh | TC-STORAGE-002 | Logged in | 1. Refresh dashboard page. | User remains logged in, role and username unchanged. | Session persists; role unchanged. | Pass | John Doe |  | High
ST-STORAGE-003 | Local storage structure | TC-STORAGE-003 | After adding a task | 1. Open browser dev tools > Application > Local Storage. | There is a key "tasks" containing array of objects with correct fields. Also "currentUser" and "role". | Structure matches spec. | Pass | John Doe |  | Medium
ST-RESP-001 | Responsive Dashboard – Tablet | TC-RESP-001 | Dashboard open | 1. Resize browser to 768px width. | Layout adapts: sidebar may collapse to icon bar or remain with reduced width; top navbar adjusts; table remains readable. | Sidebar reduces width; layout adapts. | Pass | John Doe |  | Medium
ST-RESP-002 | Responsive Dashboard – Mobile | TC-RESP-002 | Dashboard open | 1. Resize browser to 375px width. | Sidebar collapses to hamburger; main content stacks; cards stack vertically; table may scroll horizontally. | Sidebar hamburger appears; content stacks; table scrolls horizontally. | Pass | John Doe |  | Medium
ST-RESP-003 | Modal Responsiveness | TC-RESP-003 | Create task modal open | 1. Resize browser to mobile width. | Modal width shrinks to fit screen (e.g., 90% width), still usable. | Modal width adjusts; still usable. | Pass | John Doe |  | Medium